## Sheet1
What | When | Work load (man*day) | Who
Gas system installation at near EH | Anytime after |  | Princeton and
Gas cylinder pipes | EH, electronics | 2 | IHEP subcontractor
Ar switchover manifold | and gas rooms | 2
Isobutane gas cabinet | are ready | 2 | We would like IHEP
ventilation duct |  |  | gas experts get
ventilation sensor |  |  | involved in the
scale |  |  | installation.
Isobutane sensor
SF6 scale |  | 1 | Personnel needed:
R134A scale |  | 1 | Princeton (1 - 2)
Gas pipe to EH |  | 2 | IHEP (1 - 2)
Gas control crates at gas room |  | 2
Gas distribution crates at EH |  | 2
Polyflo tubing installation |  | 2
Emergency shutoff switchs |  | 2
wiring and cabling
18