## Sheet1
# | Task | Qty | Unit | Comment
1 | Make gas manifold for 6 argon cylinders. | 6 | pcs | for 3 EH, 2 for each EH.
2 | Order 6mm OD plastic tubing | 11000 | m | 3000m for each near hall, 5000m for far hall.
3 | Order flexible gas cylinder hoses with cylinder connector | 12 | pcs | for each EH need 2 for R134A, 2 for SF6.
4 | Install gas cylinder fixture for Ar. | 6 | pcs | for each EH need 2 for 6 pack Argon cylinders.
For DB near hall:
5 | Cut plastic tubing to right length, cap and label both ends | 216 | pcs | See DocDB#3749 slide #8 and #9 for length and labels.
6 | Connect the tube to RPC module and gas distribution panel | 216 | pcs | Connect one end to module, the other end to gas distribution panel.
7 | Install copper tubing from gas mixing room to EH | 1 | pcs | Clean 3/4" copper tubing, cut to right length, route tubing to flexible tray.
8 | Order and install flexible gas hose (3/4 OD), 12.3m long | 1 | pcs | S.S. braided PTFE hose, 3/4" OD, both ends are Sweglok fittings.
For LA near hall and far hall, similar to above tasks.