## Slide 1
Updated RPC Gas System Installation Plan
Changguo Lu
Princeton University

## Slide 2: Outline of the installation schedule
The tasks relevant to RPC gas system installation in MuonInstallationRLS.mpp
Gas mix room
Gas room
Gas room
Gas cabinet vent port
Gas room vent port

## Slide 3: Layout of the gas/gas mixing rooms
Wall power strip location
View direction
Wall power strip location
GC
PC

## Slide 4: Detailed plan for WBS items
3.1.12 Daya Bay near hall RPC gas system and three GC systems delivered to Daya Bay by 8/30/2010;
6.4.6 Install gas mixing/control system and 2 GC systems, DCS interface boxes, 10/8 – 11/5/2010 (we may need to start this task earlier due to the warranty deadline for 2 GCs is due on 10/21/2010)
Prerequisites:
Shipping boxes of gas mixing/control system and GCs delivered to gas/gas mixing rooms;
Network wall plugs activated;
DCS interface box cable ready, Desk for PC and GC;
Power line activated;
Water line for sprinkler installed.
Manpower:
C. Lu, (possible S. Chidzik) + Chinese labor contractor.

## Slide 5: Detailed plan for WBS items (cont’d)
Chinese labor contractor tasks:
Install gas manifolds for Argon, SF6 and R134A in gas mixing room;
Route copper gas pipe from gas mixing panel to EH1;
Hook up 6” gas ventilation pipe of the gas cabinet to gas room venting port;
Connect water pipe to gas cabinet sprinkler;
Mount emergency shut-off switch on wall and route wires to gas control panel.
Coordination with other Muon installation tasks:
Since this part of gas system installation is within gas/gas mixing rooms, it won’t interfere with any other installation tasks.

## Slide 6: Detailed plan for WBS items (cont’d)
6.4.7 Install gas distribution and digital bubbler system in 10/8 – 11/5/2010
Temporally install it in gas mixing room.
Prerequisites:
Gas racks are available.
Manpower:
Princeton will take care of this installation. Occasionally may need 1 or 2 assistants from labor contractor.
Coordination with other Muon installation tasks:
There is no foreseeable conflict with other installation tasks during this period.

## Slide 7: Detailed plan for WBS items (cont’d)
6.8 Connect gas tubing between RPC modules and gas distribution & digital bubbler crates in 12/21 – 1/10/2011.
Prerequisites:
Gas distribution/digital bubbler crates moved onto supporting structure and tested in-situ;
Utility tray on RPC module supporting structure installed.
Manpower:
Princeton supervises the installation, Chinese labor installs.
Coordination with other Muon installation tasks:
We need to coordinate with HV cable installation.
Chinese labor contractor’s tasks:
Cut plastic tubing to length and label two ends of each tube;
Connect each end to its destination connector.
IHEP may want to install support structure earlier, so this task also can be done earlier.

## Slide 8: Detailed plan for WBS items (cont’d)
6.9.2 Route Cables & Gas Lines in Flex Tray (1/18/2010 – 2/1/2011)
Prerequisites:
Gas pipe from gas mix room to EH has installed;
Gas distribution/digital bubbler racks have moved to supporting structure.
Manpower:
Princeton supervises, Chinese labor installs.
Coordination with other Muon installation tasks:
Since HV cables also need to be installed into the flex tray, we need to coordinate these two tasks.
Chinese labor contractor’s tasks:
Lay down the hose into the tray and connect each end to its destination connector.

## Slide 9: Detailed plan for WBS items (cont’d)
6.9.3 Run and test entire RPC system, 2/2/2011 – 3/30/2011
Princeton will maintain the gas system at this start-up period, locally or remotely. Right now it is still too early to make detailed plan for this task.