## Sheet1
DayaBay Schedule Status Sheet
Status as of: 4/30/08
= summary bar, no status needed
= status needed
Based on RLS v185
[5 empty] | Actual/ |  | Actual/
| Schedule |  |  | Scheduled | Forecast | Scheduled | Forecast | %
| ID | WBS No. | Task Name | Start | Start | Finish | Finish | Complete | Institution
| 406 | 1.2.1.2 | RPC Gas System | 2008-01-14 |  | 2009-09-23
1.2.1 | 407 | 1.2.1.2.1 | Final Spec & Design of RPC Gas System | 2008-01-14 | 2008-01-15 | 2008-02-28 | 2008-05-31 | 80 | Princeton
Resistive Plate Chambers | 408 | 1.2.1.2.2 | FDR/PRR Review of Gas System | 2008-02-22 | 2008-04-11 | 2008-02-26 | 2008-05-31 | 90 | Princeton
| 409 | 1.2.1.2.3 | Procure components for 1st Gas Sys | 2008-03-31 | 2008-04-01 | 2008-07-29 |  | 40 | Princeton