# Review of NF-IDS Targets Work Programme Status

C. Densham, RAL, 17 November 2009

EUROnu WP3 (selected)

| Del. No. | Deliverable name | Estimated staff months | Delivery dd-mm-yyyy |
| --- | --- | --- | --- |
| D18 | […] Evaluation of reference design for spent proton-beam handling system, including a performance analysis. Recommendation of reference design | 56 [part] | 31-11-2011 |

IDS-NF Target system

| Del. No. | Deliverable name | Estimated staff months | Delivery dd-mm-yyyy |
| --- | --- | --- | --- |
|  | The target task encompasses the liquid-mercury-jet delivery and recirculation system; the proton-beam/mercury jet interaction region; the collection of nested solenoids that collects the pions and produces a pion beam with a large energy spread in three 2 ns bursts |  |  |
| CDR | Seminal? (Immaculate?) Conceptual Design Review – the ‘start of the engineering’ |  | 10-04-2009!! |
| IDR | Cost estimate at 50-75% level |  | 31-03-2011 |

## Neutrino Factory Target System Work Programme

| Baseline liquid mercury target and beam dump | Suggested involvement / responsibility | Status |
| --- | --- | --- |
| Make statement of IDS-NF baseline specifications |  | done |
| Evaluate mercury handling infrastructure requirements, in particular revisions from Study2 |  |  |
| Evaluate costing in light of IDS-NF scenario revisions incorporating actual costs of SNS and JSNS and other relevant facilities, involving estimating: | ORNL? FNAL |  |
| Active volume of target station |  | ? |
| Mass and cost of steel and concrete shielding |  | ? |
| Cost of solenoid system |  | ? |
| Cost of civil engineering, building and services |  | ? |
| Cost of mercury system |  | ? |
| Cost of remote handling systems including shielding required |  | ? |
| Any other significant costs |  | ? |
| Beam window study | CJD, MR, MDF (RAL) | Just starting |
| Incorporate HARP data into MARS/FLUKA/GEANT4 simulations | NM,GC | Underway? |
| Pion/muon acceptance studies | HK, SB (RAL), JB (Warwick), GS | ? |
| Continue analysis of MERIT data on proton beam/liquid metal jet interactions | HK (BNL), KM (Princeton) GS (Sheffield) | Done? |
| Extend MERIT MHD simulations | RS | Done? |
| Mercury nozzle studies | RE(RAL), HK | Just starting? |
| Mercury erosion experiments for bore & nozzle | VG? | ? |
| Baseline liquid mercury beam dump, decay solenoid and shielding system studies including: | CJD, TD, OC, PL (RAL), VG(ORNL) |  |
| Beam interactions with liquid beam dump, options for mitigation of splashing, erosion etc | TD | Stalled |
| CFD studies of mercury jet interactions (splash) with dump & containment | TD | Stalled |
| Studies of irradiation, heat loads and cooling of decay solenoid | JB, PL | Underway |
| Heat loads and cooling of shielding | PL | Stalled |
| Solenoid system engineering, magnetic loads | PL | Stalled |
| Develop engineering layouts for target station including: | ORNL/FNAL/RAL |  |
| Mercury handling and recirculation system | VG | Underway |
| Beam windows + remote maintenance | CJD, MR | Not started |
| Integration of mercury jet with capture solenoid, containment and shielding including concepts for remote maintenance | VG | Underway? |
| Integration of beam dump with decay solenoid, containment and shielding including concepts for remote maintenance | VG | Underway |
| Material compatibility with Hg | ? | ? |

Cost models = generic for SB, NF, Eurisol

| Alternative target technologies (I) re-circulating solid tungsten target | Suggested involvement / responsibility | Status |
| --- | --- | --- |
| Interpretation of RAL off-line shock tests (VISAR data?) | JRJB (RAL), GS (Sheffield) | Done |
| On-line tungsten experiments (ISIS? BNL? ISOLDE?) | JRJB (RAL)? | Stalled? |
| Conceptual design for a horizontal axis spokeless solid-target wheel: | JRJB | Ongoing |
| Radiation or water cooling |  |  |
| Drive & support system |  |  |
| Beam window integration (or no beam windows) |  |  |
| 4.2.4 Optimisation of ‘Helmholtz’ type geometry with the goal of minimizing the field dip in the target region. | JB | Ongoing |
| 4.2.5 Develop a conceptual structure design for the Helmholtz magnet, which provides an entry/exit route for a solid target. | PL | No |
| 4.2.6 Develop concept for beam dump within solenoid coils | ? |  |
| 4.2.7 Remote dump: investigate the possibility to engineer the solenoid coils in such a way to let the beam pass through a “gap” to reach a remote beam dump. | SB (RAL)? |  |
| Study heating of coils & shielding due to disrupted beam | ? |  |
| 4.2.8 Investigate factors affecting the (huge) inter-coil forces, and how to reduce/handle these. | PL (RAL) | No |
| 4.2.9 Estimate active volume of system and cost implications for TS shielding | ? |  |
| 4.2.10 Investigate remote handling concepts and cost implications | RE | Started? |

| 4.3 Alternative target technologies (II) flowing tungsten powder |  |  |
| --- | --- | --- |
| 4.3.1 Agreed comparison of pion capture efficiency for reduced density powdered target with optimised system including accelerator and target geometry. | JB (Warwick) |  |
| Carry out tungsten powder handling and erosion tests using RAL test plant. | CJD, OC, PL | Ongoing |
| Develop concepts for integration with capture solenoid, proton beam entry and exit windows of (i) open powder jet and (ii) contained powder jet | CJD, OC, PL | Ongoing |
| Develop and investigate concept for beam dump – stopping target? | CJD, OC, PL, JB | Starting? |
| Investigate concept for remote beam dump involving gap in capture/decay solenoid system | CJD, OC, PL, TD, SB (RAL) GS (Sheffield), JB (Warwick) | Remove? |
| Develop concept for complete powder target recirculation system | CJD, OC, PL (RAL) |  |
| Estimate active volume of system and cost implications for TS shielding | CJD, OC, PL (RAL) |  |
| Investigate remote handling concepts and cost implications | CJD, OC, PL (RAL) |  |
| Powder jet density measurements | CJD, OC (RAL), GS (Sheffield) |  |
| On-line shock test of tungsten powder in helium at CERN? | CJD, IE |  |

Glossary of contributors

AL	Andrea Longhin (CEA Saclay)

CJD	Chris Densham (RAL)

MR	Matt Rooney (RAL)

MDF 	Mike Fitton (RAL)

NM	Nikolai Mokhov (FNAL)

GC	? (CERN)

HK	Harold Kirk (BNL)

KM	Kirk MacDonald (Princeton)

SB	Steven Brooks (RAL)

JB	John Back (Warwick)

GS	Goran Skoro (Sheffield)

RS	Roman Samulyak (FNAL)

RE	Rob Edgecock (RAL)

VG	Van Graves (ORNL)

OC	Otto Caretta (RAL)

PL	Peter Loveridge (RAL)

TD	Tristan Davenne (RAL)

JRJB	Roger Bennett (RAL)

IE	Ilias Efthymiopoulos (CERN)

## Selection criteria for choice of target technology for a Neutrino Factory and a Superbeam

|  | Criteria | Driving factors | Inputs & Issues (Nufact) | Inputs & Issues (Superbeam) |
| --- | --- | --- | --- | --- |
| 1. | Performance (I) Pion production and capture efficiency | Material Z Beam-target interaction geometry | High Z favoured | Target diameter and performance as function of material Z |
| 2. | Performance (II) Proton beam parameter limits (energy, power, pulse structure) |  | Baseline accelerator parameters 4 MW, 10±5 GeV | Baseline accelerator parameters SPL: 4 MW, 3-5 GeV CERN PS2: ? MW, 30-50 GeV |
| 3. | Performance (III) Engineering practicality, reliability | Integration with capture system Integration with beam window Integration with Beam Dump Time to repair/replace target system, Remote Handling complexity Maintenance intervals Failure scenarios & consequences of target failure | Integration with capture solenoid Near or far dump? | Magnetic horn outline design geometry & target location Far dump? |
| 4. | Cost | Target system active volume – civil engineering, shielding and building costs Remote handling complexity Target replacement and disposal cost Target replacement and disposal frequency | Need cost models: SNS, JSNS costs | Need cost models: T2K costs |
| 5. | R&D requirements (I) Off-line | Feasibility, reliability Time and investment | MERIT@ORNL RAL shock tests RAL powder jet plant |  |
| 6. | R&D requirements (II) On-line | beam interactions with materials radiation damage radiochemistry | Need to use existing facilities: MERIT data, SPS@CERN? AP-0@FNAL? SNS, JSNS, BNL | Need to use existing facilities: T2K, BNL, SPS@CERN? AP-0@FNAL? |
| 7. | Regulatory, safety, environmental issues | Liquid metal, solid, powder Site | SNS, J-SNS, Eurisol experience | SNS, J-SNS, Eurisol experience |

## 2	Basis of Cost Estimate

In order to achieve the stated requirement of a cost estimate to 50-75%, it will be necessary to:

- Determine the scope of the costing and division of responsibilities with the rest of the facility, e.g.

  - Scope: build only; build and operate; or build, operate and decommission

  - Required lifetime of facility (20 years?)

  - Envelope definitions with proton driver and muon front end

  - Level of detail required for civil engineering specifications etc

  - Regulatory issues and costs – site specific

- State basis of estimate with reference to above scope

  - statement of assumptions, effect of location, existing infrastructure etc.

  - use of previous studies and facility costs e.g. SNS, J-SNS

- Determine cost model

  - Pricing model for civil engineering, building, materials, construction, installation and commissioning

  - Shared infrastructure costs

  - Costing of institute staff

- Assess uncertainties, contingency

  - Technical risks and cost implications

- Cost implications for alternative target and beam dump technologies